## Sheet1
Hệ thống cờ tướng Online
| Trưởng nhóm : | Hoàng Trọng Phúc
| Ngày bắt đầu : | 2014-01-09
[42] | Hôm nay | 2014-06-09 | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
WBS | Tasks | Start | End | Duration (Days) | % Complete | 1/9 | 3/9 | 6/9 | 7/9 | 10/9 | 15/9 | 30/9 | 15/10 | 20/10 | 30/10 | 10/11 | 20/11 | 25/11 | 30/11 | 10/12 | 20/12 | 30/12
1 | Phân tích | 2014-01-09 | 15/9/2014 | 15 | 50%
1.1 | Lên ý tưởng - Phân tích yêu cầu | 2014-01-09 | 2014-03-09 | 2 | 100%
1.2 | Mô hình hóa hệ thống | 2014-03-09 | 2014-06-09 | 4 | 80%
1.3 | Phân chia công việc | 2014-06-09 | 2014-07-09 | 1 | 80%
1.4 | Tìm hiểu công nghệ | 2014-07-09 | 15/9/2014 | 8 | 10%
2 | Thiết kế | 15/9/2014 | 30/10/2014 | 45 | 0%
2.1 | Thiết kế CSDL | 15/9/2014 | 30/9/2014 | 15 | 0%
2.2 | Thiết kế đồ họa - Xây dựng Client-side - Xây dựng tool quản trị | 15/9/2014 | 15/10/2014 | 30 | 0%
2.3 | Xây dựng Logic và AI game | 15/9/2014 | 15/10/2014 | 30 | 0%
2.4 | Thiết kế và Xây dựng Game Service | 15/9/2014 | 30/9/2014 | 15 | 0%
2.5 | Thiết kế và Xây dựng Game Server | 15/9/2014 | 30/10/2014 | 45 | 0%
3 | Kiểm thử | 30/10/2014 | 30/11/2014 | 30 | 0%
3.1 | Kiểm thử Module - fix lỗi | 30/10/2014 | 2014-10-11 | 10 | 0%
3.2 | Kiểm thử tích hợp - fix lỗi | 2014-10-11 | 20/11/2014 | 10 | 0%
3.3 | Kiểm thử hệ thống - fix lỗi | 20/11/2014 | 25/11/2014 | 5 | 0%
3.4 | Kiểm thử chấp nhận | 25/11/2014 | 30/11/2014 | 5 | 0%
4 | Lập báo cáo | 30/11/2014 | 20/12/2014 | 20 | 0%
Note on A5: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS is automatically entered, but the formulas are different for different levels.
Note on C5: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on D5: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on E5: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. The duration is from the beginning of the Start date to the ending of the End Date. When the duration is calculated, it is calculated as End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day.
Note on F5: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).